## Slide 1: Integrated Program Management
Travis Stoner – Hexagon PPM, GBD – Projects Performance

## Slide 2: Agenda
Using earned value principles to improve forecasting for all projects
Typical challenges and gaps in an organization’s program management landscape
The building blocks of Integrated Program Management
The path to greater efficiency and accuracy, regardless of project type (e.g. FFP, IDIQ, IR&D, etc.)
Case Studies of organizations leveraging technology to achieve IPM for all projects

## Slide 3: Take-Aways
Practice EVM “right sized” as part of IPM
A common portal is key to involving all stakeholders
Commitments are key for understanding material variances
Technology is here to help the People and Processes
Report by Exception

## Slide 4: Prototypical Portfolio
Contracts with Formal EVM
~5%
~95%
Some or no EVM Requirements
Notes: Government Contractors have even more unique challenges. There is a common customer for government contractors that has some pretty stringent management and reporting rules. But these rules typically only apply to a small portion of the project portfolio. A few examples of companies you might know, in 2015 CH2M had $763m in fed contracts and overall sales of $5.3b. General Dynamics had $13.7b in fed contract revenue with overall sales of $31.4b. This is due to many different reasons ranging from the type of contract (Cost Plus, Fixed Price), the dollar amount (under $100m in the US), or the project profile (R&D vs IDIQ vs Construction) as well as Commercial aspects to their business.

## Slide 5: What is the importance of EVM?
BAC
Cumulative Cost
Time
PV (Planned Value)
AC
(Actual Cost)
CV
(Cost Variance)
SV
(Schedule Variance)
Right Now
EV
(Earned Value)
Notes: EVM allows you to visualize what being 50% complete means in relation to actual costs and schedule.
The true benefit of EVM here is that it allows the user to understand the relationship between cost and schedule to a project, allowing more informed decision making and, with regular project updates, allowing the user to distinguish between minor, expected fluctuations in a project and discrepancies that deserve attention.
As an example, let’s say the neighborhood kids have contracted out to me to build a lemonade stand. They’re going to pay be $100. And I figure it will take me 2 hours. I have my project S curve graphed. I’ve never done any carpentry, but how hard can it be?
At some point you stop to check in on your progress. Where the line meets the S curve is the “planned value” for that point, how much you think you will have completed, and how much you will have spent.
In my case, I haven’t completed as much as I had planned. I can’t find tools, I cut things wrong, I had to make trips to the hardware store, watch youtube videos on carpentry…
Earned Value is the reality check of progress. This is what I’ve produced for the time put in so far. The difference between EV and PV is Schedule Variance. As Erik will show you in the demo later, you can decide when this variance is too big and it can trigger alerts.
But that doesn’t tell you the whole story. Are you just starting some things late, or are you throwing away money to get nowhere?
In this case, the actuals are much higher than was anticipated. Not only have you gotten less done, but you’ve spent more money to do it. This is the cost variance. I didn’t just take longer, as I mentioned above, I also spent money I hadn’t anticipated, $8 for a new hammer. Very possibly a trip to urgent care.
At this point I’m wishing I hadn’t just gone and gotten the Ikea version that you put together with that little wrench. Citronsaft.
This is useful information, but it’s actually a bad example of EVM, because it’s most useful at the very beginning of a project, and here’s why.

## Slide 6: What is the importance of EVM?
BAC
Cumulative Cost
Time
PV (Planned Value)
AC
(Actual Cost)
CV
(Cost Variance)
SV
(Schedule Variance)
Right Now
EV
(Earned Value)
EAC
Projected Project Delay
(Cost) Variance at
Completion
Notes: At 20 percent completion, you can leverage EVM to create a forecast that’s accurate to within 10 percent of final costs. Giving you a clear picture of what will happen, both costs and schedule, if you stay on course.

## Slide 7: So Why Not EVM?
Define WBS
Identify the Organization
Integrate Subsystems
Identify Overhead Controls
Integrate WBS and OBS
Schedule Work
Identify Products & Milestones
Set Time-phased budget
Identify Significant Cost Elements
Establish Discrete Work Packages
Sum Work and Planning Packages
Identify Level of Effort Work
Set Overhead for Organizations
Identify Management Reserve & Unallocated Budget
Identify Target Costs and Budgets
Record Direct Costs
Organization
Planning & Budgeting
Summarize Costs in WBS
Summarize Costs in OBS
Record Indirect Costs
Identify Equivalent & Lot Costs
Perform Material Accounting
Accounting
Periodically Collect Control Account Sums
Determine Variances
Budget and Actual Indirect Costs
Sum Data and Variances
Manage Action Plans
Revise EAC
Analysis
Incorporate Changes
Reconcile Budgets
Control Retroactive Changes
Only Authorized Changes
Document PMB Changes
Revisions
EIA-748 Guidelines
Notes: So based on that, why wouldn’t anyone want to adopt EVM?
We think one of the reasons it hasn’t gained as much traction as it should, is because EVM is often conflated with rules for government compliance, for example the EIA-748 guidelines for DoD projects of $100M USD or greater.
This is the only situation where the level of rigor shown here is required. It is not representative of EVM, and it’s not necessary for an organization to effectively adopt EVM. In fact the level of detail required often prevents EVM from being applied as an effective cost management tool. It becomes an exercise of compliance.

## Slide 8: The Pillars of EVM
Budget Over Time
Actual Costs
Progress Data
Scope
Baseline Work Packages
Project
ETC
EAC
2017 EVMP Forum – August 24th & 25th
Notes: EVM adds process standards and performance metrics to a project controls framework. It does not and cannot exist separately. It builds on what you have.
For EVM to function effectively, you need four solid “pillars” of project data for it to build on.
Scope -- The key here is finding the right level of detail, and Keith will talk more about that.
Budget over Time – just like work planned vs. work completed, you need to have a clear understanding of when you expect to spend money.
Progress – you want to compare work completed against work planned, so progress is critical. When was this supposed to get done?
Actuals --
Once EV Metrics are available, they in turn, can help form additional forecast models.
An EVMS supporting multiple formulas for Estimate At Complete.
The most appropriate method can then be selected to revise forecasts or initiate changes to the project execution.

## Slide 9
Scope
Basics
Advanced
Intermediate
Keep it high level!
Define the effort.
Develop a WBS
Detail important areas
High level design
WBS Dictionary
Scope
2017 EVMP Forum – August 24th & 25th

## Slide 10
Budget over Time
Basics
Advanced
Intermediate
Hours or direct costs
Linear time phasing
Define time frames w/ sched
Add’l time-phasing methods
Resource-loaded schedule
Budget over Time
2017 EVMP Forum – August 24th & 25th

## Slide 11
Progress
Basics
Advanced
Intermediate
Percent complete
Up-front Quantitative Measurements
Milestones, Backup Data
Workflow for work owners
Progress
2017 EVMP Forum – August 24th & 25th

## Slide 12
Actual Costs
Basics
Advanced
Intermediate
High level hours/dollars
Detail targeted areas
Hours/dollars at work package level
Actual Costs
2017 EVMP Forum – August 24th & 25th

## Slide 13
Work Packages
Basics
Advanced
Intermediate
Incorporate Changes
Capture Change Approvals, Formal change tracking log
Workflows for change approvals & e-signature
Work Packages
2017 EVMP Forum – August 24th & 25th

## Slide 14: Additional Maturity Considerations
Work Authorization
Explanation of Variance/Recovery
Commitments
Forecasting
Budget Burdens

## Slide 15: EVM Right!
Right-sized EVM can be achieved with:
Establishing a solid platform for budgeting, forecasting, change management.
Defining EVM approach appropriate for contract type, project size, and/or discipline
Scoping to the appropriate level of management and control
Performing accurate and timely Progress Measurement based on standard templates and approaches.
Pulling from an integrated source of Actual Costs
Ensuring change management integrated into EVM
Matching terminology to organization culture (ex: “CPI”, “Earned/Burned”, “Productivity”)
Notes: Effective EVM is not a “one size fits all” approach. How an organization ought to implement it depends on the needs of the projects and the needs of the organization. Given this, how do you apply the “right amount” of EVM? What is the minimum EVM before we’ve stripped out too much detail? The following elements should be achieved:
Build a solid platform for budgeting, forecasting, and change management.
Use templates for WBS and progress measurement rules.
Standardize reports and views for periodic and cumulative trends.
Match EV terminology to the culture of an organization to make it accessible, user-friendly, and better understood. CPI can instead be named “Earned/Burned” or “Productivity.” Avoid the burden of using the ANSI standards when an organization has already developed its own processes and expertise.
Create a full project performance picture. This means monitoring non-EV key performance indicators (KPIs) in conjunction with EV metrics.
Develop EV metrics on a cross-section of data as appropriate – not just costs, but also hours or quantities. Then be able to roll up EV accordingly.
Document variance analysis and justification. Reporting on trends and variances alone is insufficient. Having a central record of why variances are occurring provides a stronger tool for current and future performance improvements.

## Slide 16: Learning Objectives
Standards
Coding
Collaboration / Integration
Program Management

## Slide 17
Firms tend to use multiple software platforms that are manually monitored and disconnected, which severely compromises their effectiveness.
Geno Armstrong
International Sector Leader, Engineering and Construction KPMG
Notes: Technology is the weak link. KPMG report says that organizations tend to have very well developed processes in place but the supporting technology is holding them back.

## Slide 18
Disconnected People & Systems
Chart: 
| Yes | No
Sales | 25 | 75
Access to Real-time Project Data?
Chart: 
| Yes | No
Sales | 27 | 73
Fully Integrated Project Controls System?
Chart: 
| Yes | No
Sales | 20 | 80
Owners
Contractors
Chart: 
| Yes | No
Sales | 21 | 79
KPMG: Global Construction Survey
Notes: KPMG survey
75% of owners, 74% of contractors do not have real-time access to project data.
20% of owners, 21% of contractors have fully integrated project controls systems.

## Slide 19
?
PROGRESS & PERFORMANCE
Design & Engineering
Construction
Procurement
Project Forecasts
Project Budgets
Finance
Departmental
Budgets
AFEs
/Funding
$
$
Disconnected Systems & Manual Processes
Mistakes
Version Control
Tedious Labor
Notes: When project data is not integrated, it takes a tremendous amount of manual effort to put it together for practical use. Downloading files, formatting, etc.
This requires tedious labor, leaves projects vulnerable to mistakes, and creates version control issues.
It can take the greater part of a day to produce a single project cost report.

## Slide 20
The Burden of Low-Value Work
Chart: 
| 1st Qtr | 4th Qtr
Sales | 61 | 39
61% Of time utilization
Fixing ERP issues and Labor coding
Downloading files and collating
Relying on Manual Processes:
Internal study done by EcoSys client prior to implementation
Notes: Internal study done by EcoSys client prior to implementation

## Slide 21
Disconnected People & Systems
Schedule Data
Cost Data
Visibility Challenges
Documents, Contracts
Communications, Changes
Who approved this change and why?
What do we expect our final costs to be?
Which projects are underperforming and why?
Notes: Because there is no centralized source of information, it’s difficult to know how to get answers to fundamental questions.

## Slide 22
Disconnected People & Systems
OLD
NEW
$
Can’t identify issues
Can’t make adjustments
Can’t anticipate needs
Can’t plan effectively
Projects Cost More
Projects Take Longer
Notes: Difficult to identify issues
Difficult to steer projects back on track
Difficult to anticipate resource/cash needs
Difficult to implement strategic planning
So:
Projects cost more.
Projects take longer.
And the effect snowballs. Project performance impacts future project readiness.

## Slide 23
Strategic Planning & Project Selection
Optimizing Project Performance & Efficiency
What is Integrated Program Management?
2017 EVMP Forum – August 24th & 25th
23
Notes: We’ve talked in previous webinars about the challenge of a cost/schedule divide, where different systems manage different sets of information. There is a similar sort of divide between the tactical, day to day management of project controls and the strategic, high-level management of project portfolios. Enterprise project controls is the creation of a feedback loop between the two, where project performance helps to inform selection and planning, which in term helps to ensure that the right projects are executed at the right time, ensuring better performance.

## Slide 24
What is Integrated Program Management?
Comprehensive tools and processes for effective tactical project execution
Controls for strategic planning and portfolio optimization
Notes: Comprehensive tools for tactical project execution
Plus controls for strategic planning, portfolio optimization

## Slide 25
What is Integrated Program Management?
Consistency
Visibility
Alignment
in project planning and execution
into all project data
of enterprise level strategy and day-to-day execution
Approved Projects
Resources
Budgets
Actuals
Forecasts
Performance
Notes: A connection between the two levels
Consistency in project planning and execution
Visibility into all relevant project data
Alignment of enterprise-level strategy and day-to-day execution

## Slide 26
Industry leaders are embracing Integrated Program Controls processes & tools
Planning and execution of all projects with consistent processes
Visibility of project health, issues, status, and financials
Active collaboration with all project stakeholders
Effective decision making based on the latest information
Provides project based companies with better internal controls for financials
Industry Trend
Notes: Project based businesses have unique challenges. They continuingly operate on efforts that are unique, can have a ton of risk, have large manpower and material needs, and generally have many unknowns involved. In contrast, companies that create and sell a product do the same thing repeatedly, with arguably less risk. Now, I am not saying that all business does not have risk but I am saying that I think that a business that runs projects, continuingly doing things that have never been done before, these companies need better controls and processes to manage their business. Companies that do not have good control end up in the news because they are missing their revenue or profit projections or even worse restating their financials due to a material weakness of internal controls over financial reporting.

## Slide 27
Business Friendly Design
Program Finance
Portfolio Manager
Control Account Manager
Tailored User Experience
Collaboration
Filtered Information

## Slide 28
State of the Art Solution
Off-the Shelf, Configurable
Graphical Charts & Dashboards
Dynamic Business Intelligence
Drill-Down to Any Level of Detail
Output to Multiple Formats (PDF, Excel, Word, XML)
Automated and User-Initiated Reporting
Browser based for end users

## Slide 29
Increased Efficiency
Improved Cost Performance
Accelerated Revenue
The Impact of Integrated Program Mgmt

## Slide 30
Efficiency Gains
Chart: 
| 1st Qtr | 4th Qtr
Sales | 61 | 39
Chart: 
| 1st Qtr | 4th Qtr
Sales | 10 | 90
70% – 80% increase in productivity
A Single Source of Integrated Data
Automated Reporting and Alerts
Right-sized Processes
Templates
Low-value work

## Slide 31
Improved Cost Performance
Portfolio Optimization
Contract Management
Change Management
    “Choosing the right combination of projects and eliminating wasteful ones” leads to savings of 7.4% of project spend
  McKinsey, “Infrastructure Productivity: How to Save $1 Trillion a year”, January 2013
    “Proper structuring, monitoring and enforcement of contracts leads to 9% savings on contract values”
  - International Association of Contract and Commercial Management (IACCM)
    With low use of change management, average cost growth is 10.2 %
    With high use of change management, average cost growth is -1.2%
  - Construction Industry Institute, “CII Best Practices Guide: Improving Project Performance”
Notes: To do: add graphic below illustrating how the listed % would impact portfolio spend suggesting ROI.

## Slide 32
?
PROGRESS & PERFORMANCE
Design & Engineering
Construction
Procurement
Project Forecasts
Project Budgets
Finance
Departmental
Budgets
AFEs
/Funding
$
ENTERPRISE PROJECT CONTROLS
AUTOMATED INTEGRATIONS
i
i
i
i
REAL-TIME VISUALIZATION
Fully Integrated Project Data
Notes: EcoSys EPC breaks down silos, bringing in all project data.

## Slide 33: Ball Aerospace
Headquarters: Broomfield, Colorado
Industry: Aerospace & Defense
Employees: 2,800
Top Objectives
Resolution
Key Benefits
Additional Info
12
Systems replaced by EcoSys EPC
To gain continued recognition for excellence in project execution – a necessity for success in the complex engineering world of satellites, spacecraft and their affiliated systems.
Continuous improvement of internal processes and systems in order to drive project excellence and ultimately satisfied customers and profitable operations.
Standardize data at an enterprise level, and spend more time doing value-added analysis.
Selected EcoSys as an enterprise solution to manage program costs across company.
EcoSys replaced existing estimating and pricing systems and replaced or consolidated multiple existing Ball software systems to supply integrated program management and business management processes and systems.
Ball can report and analyze program data in a consolidated fashion, and at deeper level than before.
Eliminated complexity
Leveraged Ecosys’s flexibility to match existing, proven business processes
Realized greater insights to predict and improve outcomes on active projects, while achieving the flexibility and intelligence to adapt long-term strategy at the program/organizational level over time.
Ball has been able to develop new metrics to help assess what is driving their business.
Software Use: United States

## Slide 34
Some know us for the glass jars that bear our name.
Some know us for metal packaging for food, beverage and consumer goods.
Some know us for ground-breaking aerospace and defense solutions.
All our customers know we are there to help them succeed – no matter the challenge or mission.
FROM JARS
TO STARS

## Slide 35: Ball Finance
Project Controls
Accounting
Financial Planning & Analysis
Contracts
Government Accounting & Compliance
Earned Value
Cost Estimating
Risk Analysis
Change Control
Program Planning
Budgeting
Life Cycle Management
Scheduling
SBU Reporting and Analysis
Fee Accrual Analysis
Opportunity Management
Resource Planning
Finance Organization provides support to
4 Business Units and ~ 400 Active Programs

## Slide 36: Tool Overview Prior to EcoSys
Contract Data
Program / Proposal Estimates
Opportunity Tracking
Fee Accrual Tracking
Consolidated Reporting
Pricing Rates
Program Life Cycle Mgmt
Off-The-Shelf
Home Grown
Actuals
(Costpoint)
Resource Data
GPS
Earned Value
MPM
Risk Mgmt
IRIS
Each cylinder represents a separate tool.
Interfacing existed, but no Integration.

## Slide 37: Vision for Future
Actuals
Contract Data
Resource Data
Costpoint
GPS
Program / Proposal Estimates
Consolidated Reporting
Opportunity Tracking
Fee Accrual Tracking
Pricing Rates
Earned Value
Resource Planning
Program Life Cycle Mgmt
Risk Mgmt
Phase 1: Estimation and Pricing
Phase 2: Forecast Management
Phase 3: Performance Management
Phase 4: Execution Management
EcoSys

## Slide 38: Current Configuration Overview
Detailed Estimating / Reporting
Consolidated Reporting
Opportunity Mgmt
Fee Accrual Mgmt
Configuration Optimization
Earned Value
Resource Planning
Portfolio Dashboards
Variance Analysis
Phase 1: Estimation and Pricing
Phase 2: Forecast Management
Phase 3: Performance Management
Configuration
Actions: ~3700 (Batches: ~700)
Spreadsheets: ~1600
Reports: ~800 (Batches ~70)
Formulas: ~1600
Screen Layouts: ~400
Forms: ~150
Charts: ~30
Menus: ~125
Custom Fields: ~200
Category Fields: ~170
Usage
Versions: ~170
Cost Objects: ~390,000
Actual Transactions: ~13.3M
Working Forecast Transactions: ~94M
Users: ~530

## Slide 39: Efficiencies Gained
Only system at Ball that automatically integrates Actuals, Forecast, and Budgets.
Simplification of Pricing Rate Updates
Configuration Updates do not require IT support
Integration of external metadata is automated
  Resource (GPS) Information
  Contracts System Information
  Program WBS Information (Costpoint)
Eliminates need for server surfing for the correct data

## Slide 40: Lessons Learned
Requirements Definition
  Struggle to get “Desired Output” vs “This is exactly how the Current tool works”
Cultural Issues
  Difficult transition for end users used to using MS Excel who have no stake in consolidated information
  Analysts are rewarded for being able to take data out of various systems and present data custom configured to their programs’ desires.
Amount of data
  Original design did not anticipate the amount of transactions/wbs elements that would be involved.
  Original design did not anticipate amount of data that would be pulled with single reports.
    We’ve spent a lot of time, and still have future plans for data summarization to optimize reporting.
Simplification of Design
  EcoSys Software is easy to use, but original design included functions for every requirement ever listed. Everybody wants to do it different. Many functions needed to be simplified to allow infrequent users an opportunity to survive. This however increased the amount of configuration required since will still need to support the one-off desired functionality.

## Slide 41
Improved CHART functionality is allowing for better visualization directly in EcoSys.

## Slide 42
OPPORTUNITIES Module: Allows us to track history of Opportunity as it progresses from Pursuit, to Request for Proposal, To Contracted Program. The ability to use the COST OBJECT field for multiple purposes allows this.
Opportunity metadata helps with metrics, reporting, etc.

## Slide 43: Goals for Future
Leverage Charting functionality in EcoSys to drive more executive/director level personnel to capture data directly from database.
Leverage Workflow functionality to reduce work being done “outside” of the system
Leverage existing resource estimate and Workflow functionality to provide personnel managers with forward planning data
Move “Estimators” as close as possible to the end product

## Slide 44: CH2M
Headquarters: Englewood, Colorado
Industry: EPC, GovCon
Employees: 26,000+
Top Objectives
Resolution
Key Benefits
Additional Info
5,000
Clients in
50+ countries
Effectively manage more than 3,000 projects across a range of industries.
Create data set to identify issues and organizational behaviors in order to inform new set of best practices and raise the bar for project execution across the market.
Standardize project controls to prevent business units from using disparate project delivery systems and spending money on point solutions that couldn’t be replicated.
Find a tool flexible enough to meet current needs and help them build into the future.
After in-depth industry search, CH2M selected EcoSys for its high configurability and for the industry expertise that EcoSys provides.
Leveraging EcoSys for capital project management, portfolio management, earned value, progress measurement, contract changes, and eventually resource management as well.
Interfaces with Oracle ERP system, internally developed estimating tool, and Business Intelligence system.
EcoSys is a competitive differentiator for CH2M in the market as it helps them deliver stronger capital projects.
EPC is helping them more intelligently leverage big data and ultimately leading to a whole new set of capabilities around gathering new insights, making smarter business decisions, and developing transparency into their business.
Software Use: Global

## Slide 45: Thank you for your time! Any Questions?

## Slide 46: Agenda
Take-Aways
Introduction
Project Overview
Earned Value Planning Process
Earned Value Executing Process
Earned Value Monitoring and Controlling Process
Challenges
Successes
EVM Takeaways